## Sheet1
Task | Remark | Start date | Finish date | Responsible | Status
Getting data from the watch to the Nosql DB |  | 2017-07-24 | 2017-08-25 | Irina | done
Meeting 1: Discussing the project goals |  | 2017-07-24 | 2017-07-24 | Irina, M Mopolo | done
Configure the smarthwatch |  | 2017-07-25 | 2017-07-25 | Irina | done
Define the application architecture |  | 2017-07-25 | 2017-07-28 | Irina | done
Create the FitBit developer's account |  | 2017-07-26 | 2017-07-26 | Irina | done
Create an Androïd application, implement all the libraries, download all necessary packages |  | 2017-07-26 | 2017-07-26 | Irina | done
Implement the OAuth2 autorization for user in the Android app (following all the rules) |  | 2017-07-27 | 2017-07-27 | Irina | done
Meeting 2: Discussing the project organization and tasks |  | 2017-07-28 | 2017-07-28 | Irina, M Mopolo | done
Creating a diagram of completed project architecture |  | 2017-07-28 | 2017-07-28 | Irina | done
Skype Meeting: defining following tasks with Sergey |  | 2017-07-31 | 2017-07-31 | Irina, Sergey | done
Implement the GET requests for getting last user's heartbeat data with API |  | 2017-07-31 | 2017-08-03 | Irina | done
Create NoSQL tables for storing personal data on each local machine |  | 2017-08-04 | 2017-08-04 | Irina, Sergey | done
Create external table for storing personal data on each local machine |  | 2017-08-17 | 2017-08-18 | Irina | done
Create Oracle SQL table for storing personal data on each local machine |  | 2017-08-17 | 2017-08-18 | Irina | done
Add new data to the profiles (questionnaire about bad habits), using Android app |  | 2017-08-11 | 2017-08-11 | Irina | done
Realize the GET requests from Android app to the future webservice |  | 2017-08-09 | 2017-08-09 | Irina | done
Create the web service methods to save the profile and heart data to the NoSQL database |  | 2017-08-07 | 2017-08-09 | Irina | done
Locate the webservice on the local machine |  | 2017-08-07 | 2017-08-09 | Irina | done
Implement the generating recommendations method to the Adnroid Application, using pollution and profile information |  | 2017-08-23 | 2017-08-25 | Irina | done
Write an algorythm for generating new profile data |  | 2017-08-14 | 2017-08-18 | Irina | done
Write an algorythm for generating new cardiac data |  | 2017-08-21 | 2017-08-25 | Irina | done
Getting data semi-real pollution data from PACA website |  | 2017-07-28 | 2017-08-18 | Irina, Sergey | done
Ask Air Paca about existing the API |  | 2017-07-28 | 2017-08-03 | Sergey | done
Create NoSQL table for storing daily pollution data |  | 2017-08-04 | 2017-08-04 | Irina | done
Create a method for a web service to get and save the data from AirPaca to the database |  | 2017-07-31 | 2017-08-04 | Sergey | done
Create external table for storing daily pollution data on each local machine |  | 2017-08-17 | 2017-08-18 | Irina | done
Create Oracle SQL table for storing daily pollution data on each local machine |  | 2017-08-17 | 2017-08-18 | Irina | done
Writing the specifications for analysis |  | 2017-08-02 | 2017-08-11 | Irina, Sergey | done
Specification for analyze only profile data |  | 2017-08-02 | 2017-08-04 | Irina, Sergey | done
Specification for displaying profiles (ordering data, using some group operation) |  | 2017-08-02 | 2017-08-04 | Irina | done
Specification for prediction on health problems |  | 2017-08-02 | 2017-08-04 | Irina, Sergey | done
Specification on prediction on lifetimes |  | 2017-08-02 | 2017-08-04 | Irina, Sergey | canceled
Specification on analyze with profile data and old data |  | 2017-08-07 | 2017-08-11 | Sergey | canceled
To define the Data Mining methods using generated profile data to predict the cardiac activity and to search the correlation between real pollution data and personal data |  | 2017-08-11 | 2017-08-18 | Irina | in progress
Implementation the data analysis with R |  | 2017-08-18 | 2017-08-30 | Irina | done
Analyze with only profile data |  | 2017-08-18 | 2017-08-18 | Irina | done
Displaying profiles (ordering data, using group operatons) |  | 2017-08-21 | 2017-08-22 | Irina | done
Making prediction on cardiac activity |  | 2017-08-22 | 2017-08-30 | Irina | done
Making prediction on group of risk using classification |  | 2017-08-22 | 2017-08-28 | Irina | done
Research on relation between the quality of air and personal cardiac activity (using generated data) |  | 2017-08-24 | 2017-08-25 | Irina | done
Implementation the data analysis with Oracle Olap/Datamining SQL |  | 2017-08-18 | 2017-08-28 | Sergey | ???
Analyze with only profile data |  | 2017-08-18 | 2017-08-18 | Sergey | ???
Displaying profiles (ordering data, using group operatons) |  | 2017-08-21 | 2017-08-22 | Sergey | ???
Making prediction on cardiac activity |  | 2017-08-22 | 2017-08-23 | Sergey | ???
Research on relation between the quality of air and personal cardiac activity (using generated data) |  | 2017-08-24 | 2017-08-25 | Sergey | ???
Analyze with profile data and old data |  | 2017-08-28 | 2017-08-28 | Sergey
Wriring a report |  | 2017-08-28 | 2017-09-01 | Irina | done